## Slide 1: Transferring UH Revolving Accounts at RCUH to UH
September 29, 2022
Office of the Vice President for Research and Innovation

## Slide 2: Agenda
UH Revolving Funds at RCUH
Reason for Transferring the Accounts from RCUH to UH
Initial Screening Criteria and Results
Next Steps for Revolving Fund Committee (RFC)
How to Prepare – Project Manager (PM) and Designated UH Official (DUO)
Timeline
Additional Concerns / Questions

## Slide 3: UH Revolving Funds at RCUH
Revolving Fund Accounts currently established as RCUH Projects which include Specialized Service Facilities and Recharge Centers should be transferred to UH by establishing an institutional account
Special Fund Service Center accounts should be established at UH using HRS § 304A-2157 (UH Auxiliary Enterprises Special Fund) as the legal authority
Accounts that do not comply with AP 12.204 must be restored to compliance or will be recommended for closure
All accounts must be transferred by July 1, 2023
Accounts remaining at RCUH after July 1, 2023 will be frozen

## Slide 4: Reason for Transfer
Ensure compliance with Federal regulations (2 CFR 200.468) and UH policies and procedures (AP 12.204)
Findings of excessive rates and fund balances have resulted in fines and penalties at:
  Florida State University ($3 million repayment) for unallowable charges, including lack of oversight on specialized service facilities
  University of Connecticut ($2.5 million – repayment and penalty) for failure to revise billing rates, lack of internal controls
Implement oversight and ongoing monitoring program by UH
Promotes transparency for Financial Reporting, BOR, Legislators and general public

## Slide 5: Review of Existing Revolving Accounts - Criteria Overview
Meets
Offering technical shop type, specialized facilities, or personnel services
Conducting workshops or conferences
Selling commodities generated under research projects or conferences; journals
Does not meet
Accepting and conducting sponsored research or training grants or contracts via revolving fund
Conducting a for profit activity
Conducting instruction or student activity for degree or credit
Idle activities

## Slide 6: Results of Screening
Note: Balances as of January 31, 2022
Of the 256 revolving funds accounts that meet the criteria, 191(75%) have a positive cash balance totaling $21,145,075 and 36(14%) have a deficit balance totaling $5,387,079
 | # of Accounts | FYTD Revenues | FYTD Expenses | Cash Balance
Meets | 256 | $17,159,741 | $13,243,083 | $15,758,895
Does Not Meet | 104 | $ 2,908,494 | $ 3,887,922 | $ 5,369,019
Total | 360 | $20,068,235 | $17,131,006 | $21,127,914

## Slide 7: Next Steps RFC: Address “Does not Meet” Accounts
Reason | Solution
Sponsored research or training activity | Process as an extramural award through ORS
For profit activity | Open under Commercial Enterprises Revolving Fund
Instruction or student activity | Treat like other instructional or student activity programs at UH and record tuition and fee revenue to Tuition and Fee Special Fund or appropriate student activity accounts
Idle account | Close

## Slide 8: Next Steps RFC (continued)
Revise applicable policies and procedures to clarify allowable revolving fund activities, address treatment of surplus/deficits and implement monitoring and enforcement procedures
Contact projects to address “Do Not Meet” accounts
Develop action plan to reduce surplus or clear deficit in accounts, including methodology to establish rates (tiered approach to reducing surplus based on balances and nature of activity)
Develop procedures and implement system modifications to move accounts from RCUH to UH with service orders to RCUH for personnel and procurement transactions, similar to extramural funds
Develop and conduct training on the revised process as well as refreshers on recharge center rate setting and management for faculty, staff and RCUH
Ensure accounts at RCUH are transferred to appropriate fund accounts at UH (i.e. UH Auxiliary Enterprise Special Fund) by 6/30/2023.

## Slide 9: How to Prepare – PM and DUO
Review for compliance with AP 12.204
Close revolving fund accounts that are idle or are no longer needed
  Transfer cash balances to a department’s administratively established account
Review and adjust rates to ensure a cash balance of no more than 60 days of working capital
Clear deficits – according to RCUH policy 1.300 projects shall not have a continuous (defined as six months or more) deficit

## Slide 10: Timeline
July 2022 to March 2023
January 2023
Implement monitoring plan for remaining “Meets” accounts
April to June 2023
Transfer remaining accounts from RCUH to appropriate fund at UH
Conduct Training
Address Surplus/Deficits in accounts and develop resolution plan
Transition or close “Does not Meet” Accounts
July to October 2022
Update Revolving Fund policies and procedures
Hire personnel for Revolving Account oversight role
Implement system modifications

## Slide 11: Contact and Additional Information
Email orscomp@hawaii.edu with questions / comments
Issues and details are still being addressed but if you would like to request a separate meeting please contact orscomp@hawaii.edu
Check ORS website for periodic project updates and a recording of this session